## KPI
KPI | values | units | sub | subUnits
Total Rig Hours | 2415 | hrs | 100.625 | days
Total NPT Hours | 359 | hrs | 14.9583 | days
Overall NPT % | 14.87% | %
Total NPT Cost ($) | 3895010.3583 | $
Productive Hours | 2056 | hrs | 85.6667 | days
Productive Time (%) | 85.13% | %

## mon_npt
Month | NPT (Hrs) | NPT Cost ($)
2026-05-01 | 216 | 2137405.5066
2026-06-01 | 143 | 1621039.6915
2026-07-01 | 11.5 | 136565.1602
Formulas:
NPT (Hrs) = SUMIFS([1]!NPT[Hours (hr)], [1]!NPT[Date], ">=" & [Month], [1]!NPT[Date], "<=" & EOMONTH([Month],0))
NPT (Hrs) = SUMIFS([1]!NPT[Hours (hr)], [1]!NPT[Date], ">=" & [Month], [1]!NPT[Hours (hr)], "<=" & EOMONTH([Month],0))
NPT Cost ($) = SUMIFS([1]!NPT[NPT Cost ($)], [1]!NPT[Date], ">=" & [Month], [1]!NPT[Date], "<=" & EOMONTH([Month],0))

## mon_npt_cost
Category | Sum of Hours (hr) | Sum of NPT Cost ($)
May | 216 | 2137405.5066 | May | 216 | 2137405.5066
Jun | 131.5 | 1621039.6915 | Jun | 131.5 | 1621039.6915
Jul | 11.5 | 136565.1602 | Jul | 11.5 | 136565.1602

## cat_npt
Category | Sum of Hours (hr)
Human Error | 140 | Human Error | 140
Equipment Failure | 132 | Equipment Failure | 132
Mechanical | 70.5 | Mechanical | 70.5
Mud / Solids | 11 | Mud / Solids | 11
Wellhead | 4 | Wellhead | 4
Cementing | 1.5 | Cementing | 1.5

## par_npt
Responsible Party | Sum of Hours (hr)
Clinton | 11 | Clinton | 11
Geowell | 140 | Geowell | 140
SMS Joy | 153 | SMS Joy | 153
TBD | 48.5 | TBD | 48.5
Mega Field | 1 | Mega Field | 1
MultiChase | 1.5 | MultiChase | 1.5
Ulla | 4 | Ulla | 4

## phase_npt
Phases | Sum of Hours (hr)
Conductor Piling/Cleanout | 2.5 | Conductor Piling/Cleanout | 2.5
17-1/2" x 23" Hole Section | 188.5 | 17-1/2" x 23" Hole Section | 188.5
16" Hole Section | 44 | 16" Hole Section | 44
12 1/4" Hole Section | 119.5 | 12 1/4" Hole Section | 119.5
Perforation and Wellbore Cleanout | 1 | Perforation and Wellbore Cleanout | 1
Completions | 3.5 | Completions | 3.5